## Sheet2
Action item | Recipients | Notes | Status | Column 1 | Start date | Deliverable
Request Updated Stair Photos from Architect | William Murphy (Architect) | Needed for environmental compliance visuals and submission packet | In progress |  | 2025-07-22
Verify Interest-Bearing Account Is Active | Internal | Required by DCEO to track interest on capital advance | In progress | matthew.mcmunn@gmail.com | 2025-07-25
Submit BEP Utilization Plan OR Waiver Request | Modou Cham (DCEO) | Needs vendor outreach or waiver documentation | Not started |  | 2025-07-26
Draft BEP Compliance Memo (if waiver path taken) | Modou Cham (DCEO) | Needs vendor outreach notes & RFQ copy | Not started |  | 2025-07-26
Confirm Contractor Selection and Submit to DCEO | Modou Cham (DCEO) | Needs contractor quotes and selection rationale | Not started |  | 2025-07-29
Create Final Submission Packet | Modou Cham (DCEO) | Depends on completion of all tasks above | Not started |  | 2025-08-01