## Sheet1
Action Item | Assigned To | Recipient | Why It Matters | Status | Due Date
Request Updated Stair Photos from Architect | William Melendez | Internal (William Murphy) | Needed to complete submission packet and confirm alignment with Layout B | In Progress | 2025-07-23
Verify Interest-Bearing Account Is Active | Seth Botts / Tyler | Internal | Required to manage capital advance legally; must report interest earned | Not Confirmed | 2025-07-25
Submit BEP Utilization Plan OR Waiver Request | William Melendez | Modou Cham (DCEO) | Required to meet BEP compliance before DCEO can issue Notice to Proceed | Not Started | 2025-07-26
Confirm Contractor Selection and Submit to DCEO | William Melendez | Modou Cham (DCEO) | DCEO must approve contractor before construction can begin | Pending Vendor Response | 2025-07-29
Draft BEP Compliance Memo (if waiver path taken) | William Melendez | Modou Cham (DCEO) | Documents effort and satisfies BEP goal exemption | Not Started | 2025-07-26
Create Final Submission Packet | William Melendez | Modou Cham (DCEO) | DCEO must receive full packet to release Notice to Proceed | Waiting on BEP/Contractor | 2025-08-01

## Sheet2
Feature | Category | Status | Owner | Size | Launch | Notes
| Category 1 | Not started |  | XS | Q1
| Category 2 | In progress |  | S | Q2
| Category 3 | Blocked |  | M | Q3
| Category 4 | Launched |  | L | Q4
XL
XXL

## Sheet3
Task | Priority | Owner | Status | Start date | End date | Milestone | Deliverable | Notes
| P0 |  | Not started
| P1 |  | In progress
| P2 |  | Blocked
| P3 |  | Completed